## Backlog
Type | ID | Title | Description | Parent ID | Acceptance Criteria
Feature | 104 | Medical Prescriptions | Enable doctors to create, manage, and track patient prescriptions
User Story | 207 | Create Prescription | As a doctor, I want to create a prescription for a patient so they can get their medication | 104 | - Select patient and add one or more medications - Specify dosage, frequency, and duration for each medication - Prescription saved with doctor's name and timestamp - PDF generation of the prescription
Task | 319 | Create Prescription database model | Define SQLAlchemy model for Prescription with fields: id, patient_id, doctor_name, created_at, notes. Also create PrescriptionItem model with: id, prescription_id, medication_name, dosage, frequency, duration | 207
Task | 320 | Build POST /api/prescriptions endpoint | Implement prescription creation endpoint that accepts patient_id, doctor_name, notes, and a list of medication items with dosage/frequency/duration. Validate that patient exists. | 207
Task | 321 | Create prescription form Vue component | Build a form component that allows selecting a patient, adding multiple medications with dosage fields, and submitting the prescription. Include add/remove medication row buttons. | 207
User Story | 208 | View Patient Prescriptions | As a doctor, I want to view all prescriptions for a patient so I can review their medication history | 104 | - List all prescriptions for a patient sorted by date - Each prescription shows medications, dosages, and prescribing doctor - Expandable detail view for each prescription
Task | 322 | Create GET /api/patients/{id}/prescriptions endpoint | Return all prescriptions for a given patient with their items, ordered by creation date descending. Include pagination. | 208
Task | 323 | Build prescription history list component | Create a Vue component showing a timeline of prescriptions with expandable cards showing medication details for each prescription. | 208