## Backlog
Type | ID | Title | Description | Parent ID | Acceptance Criteria
Feature | 101 | Patient Management System | Build a comprehensive patient management module for healthcare providers
User Story | 201 | Patient Registration | As a receptionist, I want to register new patients so their records are stored in the system | 101 | - Patient can be registered with name, DOB, contact info, insurance details - Duplicate detection based on name + DOB - Confirmation message shown after registration
Task | 301 | Create Patient model and database schema | Define SQLAlchemy model for Patient with fields: id, first_name, last_name, dob, email, phone, insurance_id, created_at | 201
Task | 302 | Build POST /api/patients registration endpoint | Implement patient registration endpoint with input validation, duplicate check, and proper error responses | 201
Task | 303 | Create patient registration form component | Build a Vue form with fields for patient info, client-side validation, and success/error feedback | 201
Task | 304 | Add duplicate patient detection logic | Implement fuzzy matching on name + DOB to detect potential duplicates before saving | 201
User Story | 202 | Patient Search | As a doctor, I want to search for patients so I can quickly find their records | 101 | - Search by name, DOB, or patient ID - Results shown in a paginated table - Search is case-insensitive and supports partial matches
Task | 305 | Create GET /api/patients/search endpoint | Implement search endpoint with query params for name, dob, id with pagination support | 202
Task | 306 | Build patient search UI with filters | Create a search bar component with autocomplete and filter options (name, DOB, ID) | 202
Task | 307 | Add patient results table with pagination | Build a data table showing search results with sortable columns and page navigation | 202
User Story | 203 | Patient Profile View | As a healthcare provider, I want to view a patient profile so I can see their complete information | 101 | - Profile shows personal info, contact details, insurance - History of visits displayed in timeline - Allergies and medications listed prominently
Task | 308 | Create GET /api/patients/{id} detail endpoint | Return full patient record with related visits, allergies, and medications | 203
Task | 309 | Build patient profile page UI | Create a detailed profile page with tabs for info, history, allergies, and medications | 203
Feature | 102 | Appointment Scheduling | Enable scheduling and management of patient appointments
User Story | 204 | Book Appointment | As a receptionist, I want to book appointments so patients can schedule visits | 102 | - Select doctor, date, time slot, and patient - Prevent double-booking same doctor at same time - Send confirmation notification to patient
Task | 310 | Create Appointment model and schema | Define model with fields: id, patient_id, doctor_id, datetime, duration, status, notes | 204
Task | 311 | Build POST /api/appointments booking endpoint | Implement appointment creation with conflict detection and validation | 204
Task | 312 | Create appointment booking form UI | Build a form with doctor selector, date picker, time slot picker, and patient search | 204
Task | 313 | Add appointment conflict detection | Check for overlapping appointments for the same doctor before confirming | 204
User Story | 205 | View Calendar | As a doctor, I want to view my appointment calendar so I can see my schedule | 102 | - Calendar shows daily/weekly/monthly views - Appointments color-coded by status - Click appointment to see details
Task | 314 | Create GET /api/appointments/calendar endpoint | Return appointments for a doctor within a date range, grouped by day | 205
Task | 315 | Build calendar view component | Create an interactive calendar with day/week/month toggle and appointment cards | 205
Feature | 103 | Notifications System | Implement notification system for appointment reminders and updates
User Story | 206 | Appointment Reminders | As a patient, I want to receive appointment reminders so I do not miss my visits | 103 | - Email reminder sent 24 hours before appointment - Reminder includes date, time, doctor name, location - Patient can confirm or cancel from the reminder
Task | 316 | Create notification service with email support | Implement a notification service that can send templated emails via SMTP | 206
Task | 317 | Build appointment reminder scheduler | Create a background job that finds appointments 24h away and triggers reminders | 206
Task | 318 | Create email templates for reminders | Design HTML email templates for appointment reminders with confirm/cancel links | 206